## Final Project
VaultScan CSPM — Final Project (4 people × 3 weeks)
Fill each teammate’s name. Cells under W1 / W2 / W3 describe what that person delivered that week on the real product (Next.js + FastAPI + AWS on Vercel).
# | Name | Final Project W1 | Final Project W2 | Final Project W3
1 |  | Week 1 — Backend foundation & AWS connection • Set up FastAPI backend (app, config, CORS) • Built connection store for Access Key + Secret + Role ARN from Settings • Implemented STS AssumeRole + Test Connection (real AWS account identity) • First scan session factory so scanner can call AWS APIs safely | Week 2 — Live scanner (lab Steps 1–10) • Implemented scanner engine checks: S3 public/BPA/encryption, open security groups, EC2 IMDSv1, IAM admin & trust Principal *, KMS/SQS/Secrets policies • Rule IDs + severity scoring for each finding • Verified live scan against real lab Role ARN returns intentional misconfigs | Week 3 — Hardening & reliability • Clear AWS errors (invalid keys, AccessDenied, missing resources) • Env/cold-start credential fallback for Vercel • Soft-skip services without permission; final scan reliability checklist • Supported team demo with stable real-AWS scan path
2 |  | Week 1 — Scan API & data model • Defined finding/scan JSON contracts used by the UI • Built scan + connection REST endpoints and scan history persistence • Shared TypeScript API client types for the frontend • Ensured POST /api/scan returns score + findings the dashboard can show | Week 2 — Real AWS Fixing options engine • Plan / dry-run / apply / rollback (Make as before) remediation flow • Live fix handlers: S3, security groups, IMDS, IAM trust, detach admin, KMS/SQS/Secrets • Apply session always AssumeRoles into Settings Role ARN (same account as scan) • Snapshots so fixes can be reversed on the lab account | Week 3 — AI notes & apply polish • Optional Grok enrichment on planned fixes • Fixed NoSuchEntity handling (wrong account = fail clearly, not fake success) • APPLY phrase / elevated fixes / re-scan after apply • End-to-end retest: plan → apply on real AWS → score improves
3 |  | Week 1 — App shell & Settings • Next.js dashboard layout and dark industrial theme • Tabs: Overview, Findings, Settings • Settings UI for Access Key, Secret, Role ARN, auth mode • Wired Save + Test Connection to backend (real credentials path) | Week 2 — Findings, Overview, Fixing options UI • Findings table (severity, rule, resource, evidence) • Overview KPIs (score, critical/high counts) • Fixing options tab: PLAN ALL, APPLY FIXES, APPLY confirm, only-safe toggle • Attack paths / vulnerability views; “REAL AWS” (not demo) messaging | Week 3 — Landing & UI polish • JARVIS-style landing hero with rotating words • Loading/error/empty states; clearer labels (Fixing options) • Responsive polish and presentation screenshots • Final UI pass so instructor can navigate scan → findings → fix alone
4 |  | Week 1 — Repo structure & docs start • Monorepo layout (frontend/ + backend/), dependencies • README and local run instructions for the whole team • Connecting-clouds / lab credentials checklist (what keys & Role ARN to use) • Draft Vercel project layout for multi-service deploy | Week 2 — Production deploy & compliance/export • vercel.json multi-service (Next frontend + FastAPI backend) + /api rewrite • Deployed production app (vault-scan-gamma.vercel.app) • Compliance registry mapping and PDF/report export from scans • Production smoke tests for scan and fix APIs | Week 3 — Presentation pack & handoff • Architecture notes (scan AssumeRole vs apply AssumeRole) • How-detection / remediator IAM docs for the audience • This team contribution sheet + Q&A prep • Demo script / short video of real scan + apply flow
Note: Name column is empty — write the 4 team members. W1 = foundation (connect + shell), W2 = core product (scan + real fix + Vercel), W3 = polish (harden + landing + presentation). All work is real AWS / real product, not demo-only.

## Who is who (optional)
Optional — map person # to name after you fill the main sheet
# | Name (same as main sheet) | Primary focus
1 |  | Backend & live AWS scanner
2 |  | Remediation engine & Fixing options API
3 |  | Frontend dashboard & landing
4 |  | Vercel deploy, reports & presentation docs